## Logframe
ADP name: | Your ADP
ADP number: | Your ADP Number
Support Office: | Your Support Office
Regional Manager: | Your Regional Manager
Fiscal Year: | FY 15 - FY 19
|  | FY15 | [11 empty] | FY16 | [11 empty] | FY17 | [11 empty] | FY18 | [11 empty] | FY19
|  | 1st quarter |  |  | 2nd quarter |  |  | 3rd quarter |  |  | 4th quarter |  |  | 1st quarter |  |  | 2nd quarter |  |  | 3rd quarter |  |  | 4th quarter |  |  | 1st quarter |  |  | 2nd quarter |  |  | 3rd quarter |  |  | 4th quarter |  |  | 1st quarter |  |  | 2nd quarter |  |  | 3rd quarter |  |  | 4th quarter |  |  | 1st quarter |  |  | 2nd quarter |  |  | 3rd quarter |  |  | 4th quarter
|  | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | April | May | Jun | Jul | Aug | Sept
Project Goal | Female and male SKYE Club members are empowered as active citizens, and equipped to transition well to adulthood.
Outcome 1 | Female and male SKYE club members have positive self-concept and future orientation.
Output 1.1 | SKYE Clubs are established and functional
Activity 1.1.1 | Translate, adapt and enrich SKYE Club curricula and tools | bar: 1st quarter Oct to 2nd quarter Jan
Activity 1.1.2 | Develop profile on youth in target communities (age, gender, education background, occupation, etc.) | bar: 1st quarter Dec
Activity 1.1.3 | Select communities and partners to implement SKYE Clubs based on pre-defined criteria | bar: 1st quarter Dec to 2nd quarter Jan
Activity 1.1.4 | Organize initial training of World Vision staff on SKYE Club model (SEED member and NHF team to deliver training) | bar: 1st quarter Dec
Activity 1.1.5 | Select SKYE Club leaders | bar: 2nd quarter Jan to 2nd quarter Feb; 4th quarter Jul to 4th quarter Aug; 2nd quarter Jan to 2nd quarter Feb
Activity 1.1.6 | Organize Initial training of SKYE Club leaders on SKYE Club model | bar: 2nd quarter Mar; 4th quarter Sept; 2nd quarter Mar
Activity 1.1.7 | Hold community events to mobilze and identify participating youth | bar: 2nd quarter Mar; 4th quarter Sept; 2nd quarter Mar
Activity 1.1.8 | Form SKYE Clubs | bar: 2nd quarter Mar; 4th quarter Sept; 2nd quarter Mar
Activity 1.1.9 | Organize motivational events for SKYE Club Leaders | bar: 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept
Activity 1.1.10 | Organize Training of Trainers event with World Vision staff and well-performing SKYE Club Leaders | bar: 1st quarter Oct
Activity 1.1.11 | Monitoring and evaluation activities
Activity 1.1.12 | Develop report on learnings | bar: 4th quarter Sept; 4th quarter Sept; 4th quarter Sept; 4th quarter Sept; 4th quarter Sept
Output 1.2 | Increased capacity of female and male SKYE Club members have to take on leadership roles.
Activity 1.2.1 | Support organization of trainings on Leadership curriculum for the youth | bar: 3rd quarter Jun to 4th quarter Sept; 1st quarter Dec to 2nd quarter Mar; 3rd quarter Jun to 4th quarter Sept
Activity 1.2.2 | Support SKYE Clubs to complete evaluation meeting | bar: 3rd quarter May; 4th quarter Aug; 1st quarter Nov; 2nd quarter Feb; 3rd quarter Jun; 4th quarter Sept; 1st quarter Nov; 2nd quarter Feb; 3rd quarter May; 4th quarter Aug; 1st quarter Dec; 2nd quarter Mar; 3rd quarter May; 4th quarter Aug; 1st quarter Nov; 2nd quarter Feb; 3rd quarter Jun; 4th quarter Sept
Activity 1.2.3 | Support SKYE Clubs to celebrate progress (motivational event) | bar: 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 4th quarter Sept
Activity 1.2.4 | Support SKYE Clubs to hold learning events (conferences) | bar: 3rd quarter May; 3rd quarter May; 3rd quarter May; 3rd quarter May
Outcome 2 | Female and male SKYE Club members have the capacity to engage with their community.
Output 2.1 | Increased capacity of female and male SKYE club members to become active citizens
Activity 2.1.1 | Support organization of initial and follow up trainings on Active Citizenship curriculum for the youth
Activity 2.1.2 | Support the SKYE clubs to implement initial one community project | bar: 3rd quarter April to 3rd quarter May; 1st quarter Oct to 1st quarter Nov; 3rd quarter April to 3rd quarter May
Activity 2.1.3 | Support the SKYE clubs to implement follow up community projects | bar: 3rd quarter Jun to 1st quarter Dec; 1st quarter Dec to 3rd quarter Jun; 3rd quarter Jun to 1st quarter Dec
Activity 2.1.4 | Support SKYE Clubs to invite guest speakers to meetings to present on the topics of Leadership and Active Citizenship
Outcome 3 | Female and male SKYE Club members have the capacity to secure a source of livelihood.
Output 3.1 | Increased capacity of female and male SKYE club members to secure employment.
Activity 3.1.1 | Collect information on labour market in target communities | bar: 1st quarter Dec to 2nd quarter Mar; 3rd quarter April to 3rd quarter May
Activity 3.1.2 | Support organization of trainings on Employability curriculum for the youth | bar: 3rd quarter Jun to 4th quarter Sept; 1st quarter Dec to 2nd quarter Mar; 3rd quarter Jun to 4th quarter Sept
Activity 3.1.3 | Support youth to identify and participate in internship or apprenticeship | bar: 3rd quarter Jun to 4th quarter Sept; 1st quarter Dec to 2nd quarter Mar; 3rd quarter Jun to 4th quarter Sept
Activity 3.1.4 | Support the SKYE Clubs to invite guest speakers to meetings to present on the topics of employability | bar: 3rd quarter Jun to 4th quarter Sept; 1st quarter Dec to 2nd quarter Mar; 3rd quarter Jun to 4th quarter Sept
Output 3.2 | Increased capacity of female and male SKYE club members to start a business.
Activity 3.2.1 | Support organization of trainings on Social Entrepreneurship curriculum for the youth | bar: 4th quarter Aug to 4th quarter Sept; 2nd quarter Feb to 2nd quarter Mar; 4th quarter Aug to 4th quarter Sept
Activity 3.2.2 | Support SKYE clubs to conduct youth-led market analyses | bar: 4th quarter Aug; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun; 2nd quarter Feb; 3rd quarter Jun; 4th quarter Sept; 1st quarter Dec; 4th quarter Aug; 1st quarter Dec; 2nd quarter Mar; 3rd quarter Jun
Activity 3.2.3 | Support SKYE clubs to implement social-entrepreneurship projects | bar: 4th quarter Aug to 4th quarter Sept; 2nd quarter Feb to 2nd quarter Mar; 4th quarter Aug to 4th quarter Sept
Activity 3.2.4 | Support the SKYE Clubs to invite guest speakers to meetings to present on the topics of social entrepreneurship | bar: 4th quarter Aug to 4th quarter Sept; 2nd quarter Feb to 2nd quarter Mar; 4th quarter Aug to 4th quarter Sept
Activity 3.2.5 | Support SKYE Club youth to develop personal business plan and provide business coaching | bar: 4th quarter Aug to 4th quarter Sept; 2nd quarter Feb to 2nd quarter Mar; 4th quarter Aug to 4th quarter Sept